## Event Tasks
BINGO EVENT TASKS
| Tasks | Who | When | Comments
General
| Secure Date | NP/LCF |  | McBean Park - 2nd Wednesday of the Month
| Insurance Coverage | LCF |  | LCF Provided
| Pay fee to reserve venue | NP |  | S395 + $100 must be paid when date is secured
| Determine how tickets will be sold | NP |  | LCF will provide Square links
| Determine ticket price | NP |  | $30 for Bingo only. $40 for Bingo plus Dinner
| Flyer Design and Printing | NP |  | Post around town. If Chamber member they can e-blast. Post on Facebook. Ensure your flyer says 21+ on it and includes the Lincoln Community Foundation logo as LCF is supporting your event.
| Have Chamber and City send out email blast | NP/LCF |  | If not a Chamber member, LCF can send out for you to the Chamber
| Determine seating arrangements/capacity | LCF |  | Lincoln Rec department will set up Tables/chairs for 240. If more is needed, please let LCF know. Pavilion can accommodate 350. 10 per table.
| Check in table/chairs, change, spread sheet for ticket presales, pens, Square card reader or swipes | NP/LCF |  | Lincoln Rec department will set up tables for Check-In, Bead table and Raffle/Bar ticket sales table.
| Change and change boxes | NP/LCF |  | Bring your own or LCF can provide. Only one is really needed and that is for Bar/Raffle ticket sales. Check-in and Beads can use a bank cash pouch.
| Decorations | NP |  | Minimize the decorations.
| Flyers/Brochure to promote your organization | NP |  | Optional. This is a good way to promote your non-profit or upcoming events. These can be placed on the table or handed out at check-in.
| Clean up Hall - Check List | NP |  | Clear tables and decorations when event if over
Dinner
| Secure Vendor/Get Pricing | NP
| Determine Volunteers Needed | NP
| Determine List of Supplies Needed | NP |  | Plates, utensils, napkins
Alcohol
| ABC License | NP |  | $50 for one day beer/wine license. Willie Preston or Kris Knutson can be your RBS certified person.
| Determine Alchol Types | LCF |  | Beer and Wine only. Seltzer drinks are ok and considered same as Beer. No GLASS containers!
| Determine Pricing | LCF |  | Water $1, Soda $2, Beer $4, Wine $5
| Single Drink tickets | LCF |  | LCF will provide
Raffle
| CA AG Raffle Permit | NP
| Sell Raffle Cards for $20 a card | NP |  | Sell at event. LCF will provide the Raffle cards
| Gather Raffle Prizes | NP |  | Suggest about 15 - 18 baskets plus One Door Prize
| Door Prize | NP |  | The volunteers selling Raffle Cards, should rip off the Door Prize ticket and place in a container at the Raffle /Drink ticket table. These need to be counted just before the Door Prize ticket is drawn as this number will be the basis for your Raffle report to the CA AG.
Heads or Tails
| Head or Tails | NP |  | Prize is 1/2 of the amount collected in Heads/Tails bead sales. Make sure to keep the funds separate from other Raffle/Drink ticket sales.
Bingo
| Secure Bingo Caller | LCF |  | Kris Knutson
| Bingo cage, balls and mat | LCF |  | KK has this
| Bingo Payouts | NP |  | $25 per game. If there are mulitple winners, each receives $25. $100 for last game. If multiple winners, the $100 is split up between the winners.
| Bingo Papers | LCF |  | LCF will provide
| Bingo Daubers | LCF |  | LCF will provide
| Set up tables and chairs | City |  | Lincoln Rec Dept provides
| Decorations/Table Coverings | NP |  | Optional - LCF has some table cloth rolls
| Raffle Prizes | NP
| Make many copies of the Bingo Game sheet | LCF |  | Make at least 100 copies. Hand out with Bingo papers and Dauber.
Next Bingo Non Profit may also want to hand out their flyer with Bingo papers and Dauber

## Volunteers
VOLUNTEERS NEEDED
Task | Low # | High # | Comment
Food Service | 1 | 2 | Busiest between 5:30 - 6:30
Bingo | 0 | 0 | Kris
Bingo Call Back | 0 | 0 | Willie
Wait Staff for Drinks | 1 | 2
Bartender | 1 | 2 | Busiest between 5:30 - 6:30
Check-In | 2 | 2 | Busiest between 5:30 - 6:30
Heads/Tails Beads | 2 | 3 | One at a table and one roving
Sell Raffle Tickets | 2 | 3 | Busiest between 5:30 - 6:30
Drink Tickets | 1 | 2 | Busiest between 5:30 - 6:30
Raffle Prize Runner | 1 | 1
Collect gagage after dinner and empty bingo paper bags | 2 | 3
Total Volunteers needed | 13 | 20
Some of these positions could overlap
Usually, 2 to 3 people from LCF will be available to help.

## Supplies
Supplies Needed
| What is Needed | Quantity
General Supplies
| Trash Bags | Provided by Rec Dept
| Plastic Table cloth rolls | Need 3 200 foot rolls or 2 300 foot rolls - LCF has some rolls of table cloths
| Paper Table runner | Need 3 175 foot rolls - LCF will supply this
| Decorations | Optional
Tape and scissors
| 2 Cash boxes or pouches | With appropriate change for bar and raffle tickets. LCF has cash boxes and pouches
| Cash/Ticket aprons | Optional but are helpful for Bead and roving Drink tickets sellers. LCF has aprons
Dinner Supplies |  | Some food vendors will supply these
| Dinner Plates | When giving caterer the number of plates to prepare, account for same-day and last minute tickets. This could be as many as 1/3 of your sales before the last week or so of your event.
Cutlery
Napkins
Food
Serving Spoons and Dishes
Gloves
Snacks/Dessert
Bar Supplies
| Beer | One can/bottle per person
| Wine | One bottle for every 4 persons.
| Wine Cups | 6 oz /10 oz cups
| Water | One bottle per person
| Soda | One can per person
| Ice | Lions Club @ $7.25 per bag
| Drink Tickets - one part | Sell for $1 each. Guest can buy what they need LCF supplies the tickets
Wine Openers
Beer openers
Bar towels
Bar Cleaner
Ice scoops
Tip Jar
| Note | ** If you have extra at the end of the night, you could sell it to the next non-profit on the list **
Bingo Supplies
| Bingo 10-card pack | LCF Supplied
| Daubers | LCF Supplied
| Paper Bags to toss used Bingo sheets | LCF Supplied
| Fly swatters (to signal a bingo) - optional | Non-profit can make something for this if they choose
Raffle Supplies & Door Prize
| Container to put Raffle Tickets in | Can use small paper bags - one per raffle prize
| 2 set of numbers 1 - X | x = number of Raffle prizes. One number goes on prize and one number goes on raffle ticket container
Baskets to package Raffle items
Celophane to cover raffle baskets
| Fillers | Extra little gifts to use as fillers for gift baskets
| Raffle Ticket Cards (25 ticket plus door prize ticket) | LCF will supply - $20 per card
Heads/Tails Supplies
| Heads/Tails Beads | Optional: Only if playing this game. Need about one strain of beads for every two people Sell for @10 each. Allow only three per person. LCF has lots of beads that can be used.
| Large Coin | To flip for game - Willie has a coin

## Change
Start-up Change - assumes about 150 people | Amt
Ones | 100
Fives | 265
Tens | 650
Twenties | 760
Total | 1775
Square devices for CC sales: LCF has these | 3 or more
Distribute above change to each of these stations: | Amt
Bar/Raffle Desk Change
Ones | 100
Fives | 100
Tens | 250
Total | 450
Check-In
Tens | 200
Total | 200
Heads/Tails - $10 per strain
Tens | 200
Total | 200
Bingo Payouts (assumes 3 winners per game)
Fives | 165
Twenties | 760
Total | 925

## Day of Event Schedule
Time | Task | Volunteers needed
2pm | Setup, cover tables, decorations, put together check-in, raffle/drink tickets tables, set out raffle prizes, set up Bingo Caller table. Training if necessary on use of Square devices Willie will set up sound system | 5 to 7 volunteers
4:30pm | Volunteer Check-in - get ready to serve dinner, sell raffle/drink tickets, do check-in, sell beads, etc. Additional training on use of Square devices if necessary. | 10 to 12 volunteers
5:30pm | Doors Open Dinner Served Bar Open Ticket/Bead Sales begin | 10 to 12 volunteers
6:30pm | Bingo Begins Ticket/Bead Sales continue Collect dinner garbage Empty Bingo Paper Bags Run Raffle prizes Drink runner(s) Cleanup of Dinner Service | 5 to 6 volunteers needed
8pm | Heads/Tails Game Starts Begin Cleanup of Check In and Raffle ticket tables. | Starts after 11th game and before Black Out Game
20:30 | Bingo Ends and Cleanup Begins | 6 - 10 volunteers needed
20:45 | Close up the hall