## Event Tasks
BINGO EVENT TASKS 04/09/25
| Tasks | Who | When | Comments
General
| Secure Date | NP/LCF |  | McBean Park - 2nd Wednesday of the Month
| Insurance Coverage | LCF |  | LCF Provided
| Pay fee to reserve venue | NP |  | S395 + $100 must be paid when date is secured
| Determine how tickets will be sold | NP |  | LCF will provide Square links
| Determine ticket price | NP |  | $30 for Bingo only. $40 for Bingo plus Dinner
| Flyer Design and Printing | NP |  | Post around town. If Chamber member they can e-blast. Post on Facebook. Ensure your flyer says 21+ on it and includes the Lincoln Community Foundation logo as LCF is supporting your event.
| Have Chamber and City send out email blast | NP/LCF |  | If not a Chamber member, LCF can send out for you to the Chamber. LCF can work with the City to get the event on their newsletter.
| Determine seating arrangements/capacity | LCF |  | Lincoln Rec department will set up Tables/chairs for 240. If more is needed, please let LCF know. Pavilion can accommodate 350. 10 per table.
| Check in table/chairs, change, spread sheet for ticket presales, pens, Square card reader or swipes | NP/LCF |  | Lincoln Rec department will set up tables for Check-In, Bead table and Raffle/Bar ticket sales table.
| Change and change boxes | NP/LCF |  | Bring your own change boxes or LCF can provide. Only one is really needed and that is for Bar/Raffle ticket sales. Check-in, Desert Auction and Beads can use a bank cash pouch.
| Decorations | NP |  | Minimize the decorations.
| Flyers/Brochure to promote your organization | NP |  | Optional. This is a good way to promote your non-profit or upcoming events. These can be placed on the table or handed out at check-in or spread out on the tables.
| Clean up Hall - Check List | NP |  | Clear tables and decorations when event if over. Dump the trash.
Dinner
| Secure Vendor/Get Pricing | NP
| Determine Volunteers Needed | NP
| Determine List of Supplies Needed | NP |  | Plates, utensils, napkins
Alcohol
| ABC License | NP |  | $75 for one day alcohol license (ABC-221). A copy of the ABC License form can be found at https://lincolncommunityfoundation.org/bingo/. Willie Preston or Kris Knutson can be your RBS certified person.
| Determine Alchol Types | NP |  | Beer and Wine only. Seltzer drinks are ok and considered same as Beer. NO hard alcohol allowed. No GLASS containers! Bingo players are not allowed to bring in their own alcohol.
| Determine Pricing | LCF |  | Water $1, Soda $2, Beer $4, Wine $5
| Single Drink tickets | LCF |  | LCF will provide
| Ice | NP/Lions |  | Lions Club has ice available on site. A separate invoice will be provided for any ice used.
| Preparation | NP |  | Bar needs to be set up by 4:30pm on day of event. Earlier if drinks need to be iced. Bar closes promptly at 7:30pm. At that point the NP should pack up the bar and take it to your transport so the bar is not a clean up task when Bingo is over.
Raffle
| CA AG Raffle Permit | NP |  | THIS IS A REQUIREMENT TO PARTICIPATE IN AN EVENT!
| Sell Raffle Cards for $20 a card | NP |  | Sell at event. LCF will provide the Raffle cards
| Gather Raffle Prizes | NP |  | Suggest about 15 - 18 baskets plus One Door Prize. Need a volunteer to organize the Raffle prizes with bags to hold the ticket in front of each prize. Raffle Prize Baskets need to be arranged by 5pm. Also need a volunteer to help deliver Raffle prizes to the winners during the event.
| Door Prize | NP |  | The volunteers selling Raffle Cards, should rip off the Door Prize ticket and place in a container at the Raffle /Drink ticket table. These need to be counted just before the Door Prize ticket is drawn as this number will be the basis for your Raffle report to the CA AG.
Heads or Tails
| Head or Tails | NP |  | Prize is 1/2 of the amount collected in Heads/Tails bead sales. Make sure to keep the funds separate from other Raffle/Drink ticket sales. Volunteers should be stationed at the Beads table and roaming the crowd to sell beads. A tally of beads sold ($) should be provided to the Bingo Caller periodically throughout the night. This will generate more bead sales.
Bingo
| Secure Bingo Caller | LCF |  | Kris Knutson
| Bingo cage, balls and mat | LCF |  | KK has this
| Bingo Payouts | NP |  | $25 per game. If there are mulitple winners, each receives $25. $100 for last game. If multiple winners, the $100 is split up between the winners.
| Bingo Papers | LCF |  | LCF will provide
| Bingo Daubers | LCF |  | LCF will provide
| Set up tables and chairs | City |  | Lincoln Rec Dept provides
| Table Coverings | LCF |  | LCF will provide White Table Coverings and White paper covering that runs down the center of the table.
| Make many copies of the Bingo Game sheet | LCF |  | Make at least 100 copies. Hand out with Bingo papers and Dauber.
Next Bingo Non Profit may also want to hand out their flyer with Bingo papers and Dauber
Desert Silent Auction
| If desired, the NP can have a Desert Silent Auction | NP |  | Deserts must be there by 4pm. Setup must be complete by 4:30pm
| Desert auction begins at 5:30 and closes at 6:15pm | NP |  | at 6:15pm - Collect the Desert Auction bid papers and present to the Bingo Caller. They will call our the winners. Station 2 people at the back bar (by the women's restroom). One will collect Cash payments and one will collect Card payments. Mark the Bid sheet as PAID. Station a 3rd person at the Desert Auction table. The winner will take this sheet to the desert auction table(s) and collect their desert.
| Deserts | NP |  | Provide about 20 deserts. Deserts that can be easily shared seem to work the best (cookies, cupcakes, brownies). Please wrap desert appropriately
| Paper plates, napkins, forks, knife | LCF
| Each desert should be accompanied by a Bid Sheet | NP |  | See sample on the LCF website. There should be one pen per desert auction bid sheet.
Minmum bid is $10 with $5 increments

## Volunteers
VOLUNTEERS NEEDED
Task | Low # | High # | Comment
Food Service | 1 | 2 | Busiest between 5:30 - 6:30
Bingo | 0 | 0 | Kris
Bingo Call Back | 0 | 0 | Willie
Wait Staff for Drinks | 1 | 2 | Last call is 7:30pm
Bartender | 1 | 2 | Busiest between 5:30 - 6:30
Check-In | 2 | 2 | LCF will provide
Desert Auction | 2 | 3 | Should be there by 4pm and the job is finished by 6:30pm. These volunteers can be reassigned or play bingo afterwards.
Heads/Tails Beads | 2 | 3 | One at a table and one roving
Sell Raffle Tickets | 2 | 3 | Busiest between 5:30 - 6:30
Drink Tickets | 1 | 1 | Busiest between 5:30 - 6:30
Raffle Prize Runner | 1 | 1 | 6:30 - 8:30
Collect garbage after dinner and empty bingo paper bags during the evening | 2 | 3 | 6:00 - 8:30
Total Volunteers needed | 15 | 22
Some of these positions could overlap

## Supplies
Supplies Needed
| What is Needed | Quantity
General Supplies
| Trash Bags | Provided by Rec Dept
| Plastic Table cloth rolls | Need 3 200 foot rolls or 2 300 foot rolls - LCF has some rolls of table cloths
| Paper Table runner | Need 3 175 foot rolls - LCF will supply this
| Decorations | Optional and unnecessary
Tape and scissors
| 2 Cash boxes or pouches | With appropriate change for bar and raffle tickets. LCF has cash boxes and pouches
| Cash/Ticket aprons | Optional but are helpful for Bead and roving Drink tickets sellers. LCF has aprons
Dinner Supplies |  | Some food vendors will supply these
| Dinner Plates | When giving caterer the number of plates to prepare, account for same-day and last minute tickets. This could be as many as 1/3 of your sales before the last week or so of your event.
Cutlery
Napkins
Food
Serving Spoons and Dishes
Gloves
Snacks/Dessert
Bar Supplies
| Beer | One can/bottle per person
| Wine | One bottle for every 4 persons.
| Wine Cups | 6 oz /10 oz cups
| Water | One bottle per person
| Soda | One can per person
| Ice | Lions Club @ $7.25 per bag
| Drink Tickets - one part | Sell for $1 each. Guest can buy what they need LCF supplies the tickets
Wine Openers
Beer openers
Bar towels
Bar Cleaner
Ice scoops
Tip Jar
| Note | ** If you have extra at the end of the night, you could sell it to the next non-profit on the list **
Bingo Supplies
| Bingo 10-card pack | LCF Supplied
| Daubers | LCF Supplied
| Paper Bags to toss used Bingo sheets | LCF Supplied
| Fly swatters (to signal a bingo) - optional | Non-profit can make something for this if they choose
Raffle Supplies & Door Prize
| Container to put Raffle Tickets in | Can use small paper bags - one per raffle prize
| 2 set of numbers 1 - X | x = number of Raffle prizes. One number goes on prize and one number goes on raffle ticket container
Baskets to package Raffle items
Celophane to cover raffle baskets
| Fillers | Extra little gifts to use as fillers for gift baskets
| Raffle Ticket Cards (25 ticket plus door prize ticket) | LCF will supply - $20 per card
Heads/Tails Supplies
| Heads/Tails Beads | Optional: Only if playing this game. Need about one strain of beads for every two people Sell for @10 each. Allow only three per person. LCF will supply the beads
| Large Coin | To flip for game - Willie has a coin
Desert Auction Supplies
| Desert Auction Bid Sheets | Copy the sheet from LCF's website
| Pens | One pen per Desert Auction Bid Sheet

## Change
Start-up Change - assumes about 150 people | Amt
Ones | 100
Fives | 370
Tens | 770
Twenties | 760
Total | 2000
Square devices for CC sales: LCF has these | 3 or more
Distribute above change to each of these stations: | Amt
Bar/Raffle Desk Change
Ones | 100
Fives | 100
Tens | 250
Total | 450
Check-In
Tens | 200
Total | 200
Heads/Tails - $10 per strain
Tens | 200
Total | 200
Desert Auction
Fives | 105
Tens | 120
Total | 225
Bingo Payouts (assumes 3 winners per game)
Fives | 165
Twenties | 760
Total | 925

## Day of Event Schedule
Time | Task | Volunteers needed
2pm | Setup, cover tables, decorations, put together check-in, raffle/drink tickets tables, set out raffle prizes. Training if necessary on use of Square devices Willie will set up sound system | 5 to 7 volunteers - Phx HS will help with this volunteer load. Talk to LCF about how they can help.
4:00pm | Desert Auction items and Raffle baskets should be in the venue | 2/3 volunteers
4:30pm | Volunteer Check-in - get ready to serve dinner, sell raffle/drink tickets, do check-in, sell beads, etc. Additional training on use of Square devices if necessary. Dessert and Raffle baskets should be set up. | 10 to 12 volunteers
5:00pm | Doors Open (Doors open at 5:30 but a few people will start showing up at 5) Dinner Service begins at 5:30 Bar Open Ticket/Bead Sales begin | 10 to 12 volunteers
6:15pm | Desert Auction closes. Collect bid sheets and be ready to accept payments for dessers
6:30pm | Bingo Begins Ticket/Bead Sales continue Collect dinner garbage Empty Bingo Paper Bags Run Raffle prizes Drink runner(s) Cleanup of Dinner Service | 5 to 6 volunteers needed
8pm | Heads/Tails Game Starts Begin Cleanup of Check In and Raffle ticket tables. | Starts after 11th game and before Black Out Game
20:30 | Bingo Ends and Cleanup Begins. Dump garbage bags in outside container. | 6 - 10 volunteers needed
20:45 | Close up the hall